## Project Data
Project Name | AI Driven Testing
Online team meeting | https://fau.zoom.us/j/69553438847?pwd=VHGm0oOZ2KvPbbhrGsmX83d4rAuuaT.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2025ss04-ai-driven-testing
GitHub feature board | https://github.com/orgs/amosproj/projects/82/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/86/views/1
Planning Poker Link | https://pokerplanning.org/room/05e2b4ba-b452-4c29-8ba0-e9ae23005ce0
Team T-shirt (white) | https://www.shirtinator.ch/s/gyMoSd27QOSllB0wUYQ7XA
Team T-shirt (black) | https://www.shirtinator.ch/s/-GuNOvW5Q2qjHFDZrYILpA
black link again since it didnt work for some | https://www.shirtinator.ch/t-shirts/gestalten/t-shirt-bedrucken#/load/share/f86b8d3a-f5b9-436a-a31c-50d9ad820ba4
Additional materials | ...
Team maling list | oss-amos-proj4@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Brüggemann | Jonas | JonasBrue | jonas.brueggemann@campus.tu-berlin.de
Clicqué | Lennard | OlafVanHuusen | lennard.clicque@fau.de
Hasse | Lisabeth | PeppermintCoding123 | lisabeth.hasse@fau.de
Heidkamp | Tessa | theidkamp | tessa.v.heidkamp@campus.tu-berlin.de
Krug | Maximilian | HaruspexSan | maximilian.krug@fau.de
Lang | Felix | xilef45 | felix.l.lang@fau.de
Lorenz | Alexander | Hydraneut | alexander.lorenz@fau.de
Parameswaran | Biranavan | Biranavan-Parameswaran | parameswaran@campus.tu-berlin.de
Takale | Aditi Vishwas | adititakale01 | adititakale01@gmail.com
Alsultan | Moaiad | Moaiadsu | m.alhmadhalsultan@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | First-Level-Support :) | Comment
1 | 2025-04-16 | both | both | all other | none | Felix | Felix
2 | 2025-04-23 | both | Max | all other | Max | Felix | Felix
3 | 2025-04-30 | Max | Alex | all other | Alex | Felix | Felix
4 | 2025-05-07 | Alex | Max | all other | Jonas | Felix | Felix | Build process review
5 | 2025-05-14 | Max | Alex | all other | Lennard | Felix | Felix
6 | 2025-05-21 | Alex | Max | all other | Lisabeth | Felix | Felix
7 | 2025-05-28 | Max | Alex | all other | Tessa | Felix | Felix | Mid-term due
8 | 2025-06-04 | Alex | Max | all other | Maximilian | Felix | Felix
9 | 2025-06-11 | Max | Alex | all other | Alexander | Felix | Felix
10 | 2025-06-18 | Alex | Max | all other | Biranavan | Felix | Felix
11 | 2025-06-25 | Max | Alex | all other | Aditi Vishwas | Felix | Felix
12 | 2025-07-02 | Alex | Max | all other | Moaiad | Felix | Felix
13 | 2025-07-09 | Max | Alex | all other |  | Felix | Felix
14 | 2025-07-16 |  |  | all other |  | Felix | Felix | Demo day!
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Interpersonal relationship objectives: “To foster an atmosphere of mutual respect and learning, creating a team-spirit”
Main goal is to create a satisfiying project that makes Us, the IP(Industry Partner) and open-source community happy
Meeting norms | Documentation in english and meeting language in German
Start on time
Be Polite
Purpose: Clearly define the goal of the meeting. Preparation: Ensure all participants are well-informed and ready to contribute. Participation: Encourage active engagement from all attendees. Process: Organize the meeting structure and agenda effectively. Progress: Monitor the meeting's progress and ensure it stays on track.
Working norms | Leave the code better than you found it (The Boy Scout Rule)
Keep it Simple, Stupid (KISS)
Coordination norms | Felix will do the retros + keeping track of meetings
Alex and Max will take care of the assignments (Backlog Items)
Communication norms | We check Discord at least every day
Consideration norms | Communicate Conflict in Team-Meeting. Help from Felix or Jovana to solve conflicts.
Respect, active listening, tolerance
Cont. improvement norms | Experimentation spirit and feedback culture
Burn-Down charts as process tracking
Rewards | Appreciation and praise
Sanctions | Wear the ducky tie
Post a cute/funny pic of a pet (or similar)
Signatures
Scrum Master | Felix Lang
Product owner | Maximilian Krug
Product owner | Alexander Lorenz
Software developer | Mohammad Moaiad Alhamdh Alsultan (Moaiad Alsultan)
Software developer | Jonas Brüggemann
Software developer | Lennard Clicqué
Software developer | Biranavan Parameswaran (Biri)
Software developer | Lisabeth Hasse
Software developer | Tessa Heidkamp
Software developer | Aditi Vishwas Takale

## Product Goal
Product Vision | Project Mission
Product Vision We are transforming the landscape of software testing through intelligent, AI-powered automation. Our vision is a future where testing is no longer a bottleneck but a seamless, continuous, and reliable part of the development process. By empowering developers and testers with AI tools that autonomously generate and maintain test cases, we free them from generating the same test cases over and over to instead focus on creative problem-solving and strategic innovation. Our solution supports a future of scalable, secure, and locally controlled quality assurance, driving the next evolution in software development. We invision the role of the programmer to become a curator and innovator of AI generated Code. | Product Mission Deliver a minimum viable product (MVP) of an AI-powered test generation assistant that interacts effectively with real-world software projects. This includes laying the empirical and research groundwork for the idea. From this research we will conclude a MVP, that can analyze simple Python and C++ programs and produce corresponding test cases. Operated through a user-friendly chat interface. The MVP will showcase initial integration with widely used open-source testing frameworks such as Robot Framework, proving the viability of AI-assisted test automation in practical, everyday development environments.

## Product Glossary
Term | Definition
LLM | Large language model
LLM Input | User Input into the LLM
LLM Output | Response of the LLM to the Input
LLM System Prompt | System message sent (this is different from the LLM Input)
Temperature | gradient how "creative" the LLM behaves
Interface Script/ LLM factory | Backbone script of the project to start, end and use the LLM containers
Container | Docker container, (not kaniko os something else)
IP | Industry Partner
Sprint | agile (Amos) sprint with a duration of 2 weeks
CI | GitHub workflows as Continuouse Integration assistent
Wiki | Documentation in the Github repos wiki (not Wikipedia)
Laptop | Personal device to run the code (nothing fancy standard device) TODO add specs

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Laying foundational architecture groundwork
5 | Initalize future development area
6 | Enhance user value by metricization
7 | Preparing for Midproject review
8 | Expanding Modularity and advancing metricization / Refactoring
9 | Enhancing accuracy of LLM return
10 | Advancing Usability and LLM response rsatistics
11 | Design and Development for own LLM
12 | Create CI Usecase and user value
13 | Prepare for demo day
14 | Last touches before the finally
15 | -/- (only winter term)

## Velocity Tracking
Sprint # | Story Points Planned | Story Points Realized
1
2 | 33 | 36
3 | 22 | 20
4 | 23 | 23
5 | 27 | 28
6 | 21 | 25
7 | 54
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Velocity chart
Sprint | Average Realized | Average Planned
1 | 26.4 | 30
2 | 26.4 | 30
3 | 26.4 | 30
4 | 26.4 | 30
5 | 26.4 | 30
6 | 26.4 | 30
7 | 26.4 | 30
8 | 26.4 | 30
9 | 26.4 | 30
10 | 26.4 | 30
11 | 26.4 | 30
12 | 26.4 | 30
13 | 26.4 | 30
14 | 26.4 | 30
15 | 26.4 | 30

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 136 | 136 | 132
Sprints
1 |  |  | 0 | 136 | 0 | 132
2 |  |  | 33 | 103 | 36 | 132
3 |  |  | 33 | 70 | 20 | 96
4 |  |  | 22 | 37 | 23 | 76
5 |  |  | 27 | 15 | 28 | 53
6 |  |  | 21 | -12 | 25 | 25
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
Finish | [5 empty] | 0
Features
1
(none since we didnt meet with the IP yet)
2
|  | Write .py script to interact with the LLM 3 | 3 |  | 3
|  | Reaserch LLM 5 | 5 |  | 5
|  | Research Deepcoder/Phi4-Mini | 5 |  | 5
|  | Reaserch LLM 4 | 5 |  | 5
|  | Reaserch LLM 2 | 5 |  | 8
|  | Create initial Architecture Documentation | 2 |  | 2
|  | Reaserch LLM 1 | 5 |  | 3
|  | Write .py script to interact with the LLM 1 | 3 |  | 5
3
|  | Continue to Maintain the Architecture-Document | 3 |  | 3
|  | Write .py script to interact with the LLM 2 | 3 |  | 3
|  | Research Code Complexity | 5 |  | 5
|  | Create Python test cases | 3 |  | 1
|  | Start Bill of Material | 1 |  | 1
|  | Continue to Maintain Bill of Materials | 1 |  | 1
|  | Write .py script to interact with the LLM 5 | 3 |  | 3
|  | Write .py script to interact with the LLM 4 | 3 |  | 3
4
|  | Continue to Maintain Bill of Materials | 1 |  | 1
|  | Unify the python interface | 3 |  | 3
|  | initialize ReadMe | 2 |  | 1
|  | Research AI-Model Benchmark | 3 |  | 3
|  | Build the first Benchmarking tests | 3 |  | 3
|  | make CI-Pipeline | 5 |  | 8
|  | Continue to Maintain the Architecture-Document | 3 |  | 2
|  | Set up Branchmanagment | 3 |  | 2
5
|  | Add Modul Interface | 5 |  | 5
|  | Research Ollama | 5 |  | 3
|  | Test docker performance | 3 |  | 5
|  | Initialize API | 5 |  | 5
|  | Build process video | 3 |  | 3
|  | Initialize Frontend | 5 |  | 3
|  | Continue to Maintain Bill of Materials | 1 |  | 1
|  | Make metrics.py into its own modul |  |  | 3
6
|  | Write .py script to start docker containers | 3 |  | 3
|  | Show POs how the Project works | 3 |  | 2
|  | Research: Spell checker | 3 |  | 3
|  | Onboard small LLM | 1 |  | 1
|  | Frontend Make User enter prompt and source code | 5 |  | 8
|  | Module: Analyze context size | 3 |  | 5
|  | Connect API to Frontend | 3 |  | 3
Leftovers
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Burndown chart
Ideal Case | Real Case | Sprint | Planned progress
|  | 1 | 136 | 136
|  | 2 | 109.6 | 100
|  | 3 | 83.2 | 80
|  | 4 | 56.8 | 57
|  | 5 | 30.4 | 39
|  | 6 | 4
|  | 7 | -22.4
ca. 30 pro sprint

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  | estimation ca. 30 per sprint | 240 | 240
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
7 |  |  | 54 | 240 | 0 | 240
8 |  |  | 30 | 186 | 0 | 240
9 |  |  | 26 | 156 | 0 | 240
10 |  |  | 30 | 130 | 0 | 240
11 |  |  | 28 | 100 | 0 | 240
12 |  |  | 26 | 72 | 0 | 240
13 |  |  | 31 | 46 | 0 | 240
14 |  |  | 15 | 15 | 0 | 240
Features
7
|  | Module. Evaluate LLM performance | 3
|  | Extract Code from Input/Output | 3
|  | Research/Implement How to include whole project | 5
|  | Module: Code Complexity MCC | 5
|  | Set up Docker compose | 5
|  | Unify Conda environment | 5
|  | Bill of Material | 1
|  | Architecture Document | 3
|  | Module CCC | 5
|  | Module: external research | 5
|  | Initialize user, (technical) design, and build/deploy documentation | 3
|  | Refactoring: unify payload to json | 5
|  | Module: CMT Code Complexity | 3
|  | Set prerequistists for Modulel | 3
8
|  | Module: Add security analyzer module for generated code | 3
3
|  | Module: Add configurable timeouts for LLM generation | 3
5
5
|  | Frontend: make modules togglable in UI | 5
|  | Module: Detect redundant/duplicate test cases | 3
|  | Output exporter (as zip, json, http etc..) | 3
9
|  | Research: test readability score (Flesch/Kincaid) | 3
|  | Module: Detect Edgecase accuracy of LLM research | 5
|  | Onboard and Test new LLM | 3
|  | Module: Map language to optimal model with fallback support | 3
|  | Module: Allow chaining outputs between models | 3
|  | Research: Befits of chaining methods | 2
|  | Use metrics to compare 1b, 3b, 7b and maybe 14b models | 2
|  | Research: How to measure code coverage with tools | 5
10
|  | Onboard and Test new LLM | 3
|  | Module: Measure test readability score (Flesch/Kincaid) | 5
|  | Module: Check output for code coverage of the tests | 3
|  | Module: Flaky Test Identifier: Detect and flag non-deterministic/generated tests | 5
|  | Module: Show dependency hierarchy of code by logic flow | 3
|  | Try HPC to run the thing and test a larger model 50b+ parameters | 5
|  | Module: Auto-split large files into units for test generation | 3
|  | Research: how to train/ enhance own LLM on HPC | 3
11
|  | Onboard and Test new LLM | 3
|  | Use HPC to train our own LLM | 5
|  | Module: Auto-group similar test cases into suites | 5
|  | Clean the repo | 2
|  | Module: LLM testing of Code understandability, make LLM describe the code, let the same LLM (with no history) build the code from the description -> see if code passes the Unit tests. | 5
|  | Test current models for output consistency (deterministic) | 3
|  | Frontend: Diff viewer between original and tested source | 5
12
|  | Research: different types of software test | 3
|  | CI: create CI for running everything in CI | 2
|  | Research: can we run the models in the CI | 3
|  | Eveluate the performance of the models with and without the modules | 3
|  | Placeholder | 15
13
|  | Ci: Create a CI flow that creates the uni tests and provides them as unit tests | 5
|  | Improve Usability of the frontend | 5
|  | Prepare Demo and create 3 Usecases | 2
|  | Clean the wiki | 2
|  | Overwork the Bill of Materials | 1
|  | Overwork the Architectuer Document | 3
|  | Refactor the Code | 3
|  | Placeholder | 10
14
|  | Clean the repo | 2
|  | Finish documentation | 2
|  | Export Documentation (Wiki) as PDF | 2
|  | Create Demo Day slide | 1
|  | Create Demo Day video | 3
|  | Finalize user, (technical) design, and build/deploy documentation | 5

## Final Project Burndown chart
Sprint | Planned progress
7 | 240
8 | 213.6
9 | 187.2
10 | 160.8
11 | 134.4
12 | 108
13 | 81.6
14 | 55.2

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
1 | # Definition of Done - [ ] document the results of your research - [ ] note if the LLM works or not - [ ] add documentation to the LLM section of the wiki - [ ] link any sources you found, preferably scientific | Project builds, deploys, and tests successfully Project is improved compared to last release Sprint release notes have been written Wiki has been updated with new knowledge | Release passes accaptence test Functional and non functional requirements are met Requirements and Use cases are covered User documentation has been updated Design documentation has been updated
2 | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment
| Python Version for running the main script | Python V | 3.11 | Python Software Foundation License Version 2
| Running Ollama via Docker | Docker | 28.1.1 | Apache License, Version 2.0.
| Ollama enables running LLMs easily | Ollama | 0.6.8 | MIT License
| Running Qwen2.5-Coder via Ollama | Qwen2.5-coder | qwen2.5-coder:3b-instruct-q8_0 | Qwen Research License (3B Model only), Apache License 2.0 (others)
| Running Mistral via Ollama | Mistral | mistral:7b-instruct-v0.3-q3_K_M | Apache License, Version 2.0.
| Running Deepseek-Coder via Ollama | Deepseek-Coder | deepseek-coder:6.7b-instruct-q3_K_M | Deepseek License Agreement | only used for testing
| Running Phi4-Mini via Ollama | Phi4-Mini | phi4-mini:3.8b-q4_K_M | MIT License
| Running Gemma via Ollama | Gemma | gemma3:4b-it-q4_K_M | Gemma Terms of Use | only used for testing
| Running Tinyllama via Ollama | Tinyllama | tinyllama:1.1b | Apache License, Version 2.0.
| devDependency | pytest | 7.4.3 | MIT License | used for unit‐tests
| Used python library | docker | 7.0.0 | Apache License, Version 2.0.
| Used python library | requests | 2.28.0 | Apache License, Version 2.0.
| Used python library | tqdm | 4.65.0 | MIT License
| Used python library | numpy | 1.22.0 | BSD License
| Used python library | pandas | 1.3.0 | BSD License
| Used python library | fastapi | 0.115.12 | MIT License
| Used python library | uvicorn[standard] | 0.34.2 | BSD License
| Python environment | conda-forge | 25.5.0 | BSD-3 License
| frontend | react | 19.1.0 | MIT License
| frontend | react-dom | 19.1.0 | MIT License
| frontend | react-scripts | 5.0.1 | MIT License
| frontend | typescript | 4.9.5 | Apache License, Version 2.0.
| frontend | web-vitals | 2.1.4 | Apache License, Version 2.0.
| Used for Code formatting | Black | 24.3.0 | MIT License
| Used for Linting | flake8 | 7.2.0 | MIT License

## Planning Poker
Last Name | First Name | Value
Brüggemann | Jonas | 5 | 5 | OK
Clicqué | Lennard | 5
Hasse | Lisabeth | 5
Heidkamp | Tessa | 5
Parameswaran | Biranavan | 5 | 0 | No size
Takale | Aditi Vishwas | 5 | 1 | Trivial size
|  |  | 2 | Small size
|  |  | 3 | Medium size
|  |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value

## ItemPlanning
Sprint | Name | Description
7 |  | Complete | User Story | Notes | Acceptance Criteria | Definition of Done
Unify requirements.txt files
Frontend: Display LLM result in Textbox
| Onboard small model 1b |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Prune models for only MIT license Models
Unify payload to Json
| Module: Evaluate LLM performance |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Implement System property findings |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Add multiple payload APIs
8
Onboard and Test new LLM
| Module: Add security analyzer module for generated code |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Add configurable timeouts for LLM generation |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Code Complexity: Complexity Measurement Tool (CMT) |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Code Complexity: CM |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Frontend: make modules togglable in UI
| Module: Detect redundant/duplicate test cases |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Output exporter (as zip, json, http etc..)
9
Research: test readability score (Flesch/Kincaid)
| Module: Detect Edgecase accuracy of LLM research |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Onboard and Test new LLM
| Module: Map language to optimal model with fallback support |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Allow chaining outputs between models |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Research: Befits of chaining methods
Use metrics to compare 1b, 3b, 7b and maybe 14b models
Research: How to measure code coverage with tools
10
Onboard and Test new LLM
| Module: Measure test readability score (Flesch/Kincaid) |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Check output for code coverage of the tests |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Flaky Test Identifier: Detect and flag non-deterministic/generated tests |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
| Module: Show dependency hierarchy of code by logic flow |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Try HPC to run the thing and test a larger model 50b+ parameters
| Module: Auto-split large files into units for test generation |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Research: how to train/ enhance own LLM on HPC
11
Onboard and Test new LLM
Use HPC to train our own LLM
| Module: Auto-group similar test cases into suites |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Clean the repo
| Module: LLM testing of Code understandability, make LLM describe the code, let the same LLM (with no history) build the code from the description -> see if code passes the Unit tests. |  |  |  |  | # Definition of Done (DoD) Checklist - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki
Test current models for output consistency (deterministic)
Frontend: Diff viewer between original and tested source
12
Research: different types of software test
CI: create Docker CI for running everything in CI
Research: can we run the models in the CI
Eveluate the performance of the models with and without the modules
Placeholder
13
Ci: Create a CI flow that creates the uni tests and provides them as unit tests
Improve Usability of the frontend
Prepare Demo and create 3 Usecases
Clean the wiki
Overwork the Bill of Materials
Overwork the Architectuer Document
Refactor the Code
Placeholder
14
Clean the repo
Finish documentation
Export Documentation (Wiki) as PDF
Create Demo Day slide
Create Demo Day video
Finalize user, (technical) design, and build/deploy documentation